## Sheet1
| Task Description | Component / Feature | Details |  | Task Description | Component / Feature | Details |  | Task Description | Component / Feature | Details |  | Task Description | Component / Feature | Details |  | Task Description | Component / Feature | Details |  |  | Task Description | Component / Feature | Details |  |  | Task Description | Component / Feature | Details |  |  | Task Description | Component / Feature | Details |  | Task Description | Component / Feature | Details
As a user, I want to be able to navigate the application, so that I may visit all parts of the application and use the features available to me within P-Alpha. | Create generic React components with state hooks and route them to the application via React Route, so that they may be utilized as necessary for the other User Tasks implementations ad hoc. | Generic React Components, React Route | Implement stateful React components using hooks and utilize React Router for routing within the application. | As a student, I want to be able to sign up (create an account) for P-Alpha so that I can have access to my personalized learning session (begin code comprehension exercises). | Create a sign-up React component, with three input fields for email and password (one is for confirmation), a checkbox associated with a hyperlink in the form of an adjacent label, rendering to P-Alpha’s Terms & Conditions, and a submit button inside a form element on the component template. Thereafter, use React Router to route the created component to ‘/signup’. | Sign-Up Component | Develop a sign-up form with specified inputs and a submit button, and route it to '/signup' using React Router. | As a student, I want to be able to sign into my P-Alpha account so that I can start doing code comprehension exercises and have a personalized learning session. | Create a log-in React component, with two input fields and a submit button inside a form element on the template (this may be expedited if an existing component is extended). Then, use React Router to route the created component to ‘/login’. | Login Component | Develop a login form with specified inputs and a submit button, and route it to '/login' using React Router. | As a teacher, I want to log into my P-Alpha Account so that I may monitor my student’s progress. | On the landing page of P-Alpha add a function that makes a GET request to discern that the user is a teacher and as such should be redirected to their correct page. | Landing Page Functionality | Implement a function on the landing page to perform a GET request to determine the user's role (teacher) and redirect accordingly. | As a student, (while I am logged into my P-Alpha account) I want to be presented with a code snippet, so that I can analyze it and give my description. [26] | Define all the possible CodeSnippets that would be available for Code Comprehension, and store them in Firebase creating appropriate documents. | Code Snippet Definition and Storage | Identify and catalog code snippets for comprehension, storing them in Firebase with corresponding documents. | 1 hour - 10 percent. [5] | As a student, after I provide my explanation to a sample code snippet, I want to be given all the test cases and their results that the generated code was run against, so that I can be informed if my explanation to a provided code snippet is valid, and if not, to see which tests the generated code failed and passed. [19] | Define tests for the code snippets and run them against each one. Refactor or modify the code snippets and tests to ensure cohesion and correctness. Upload them into the Database. | Code Snippet Testing and Refactoring | Develop and execute tests for code snippets, refactor as necessary, and upload the refined snippets and tests to the database. | 1 hour - 10 percent. [6] | As a student, I want to view a summary of my progress in the code comprehension progress as a whole, so that I can understand how well I understand the material. [16] | Implement the page that renders when a request to review this summary is made. | Review Summary Page | Develop a page that appears upon requesting to review a summary. | [4] | As a teacher, I want to retrieve a performance report of a student, so that I may assess their progress in their code comprehension abilities. | Leverage pre-defined navigation, pages, and components to render a page that allows the teacher to make this request. | Teacher Request Page | Utilize existing navigation, pages, and components to develop a page for teacher requests. | As a teacher, I want to retrieve formatted overall performance statistics, so that I may assess my students’ progress thus far. | Leverage pre-defined navigation, pages, and components to render a page that allows the teacher to make this request. | Teacher Request Page | Utilize existing navigation, pages, and components to develop a page for teacher requests.
| Create a React component called Dashboard which is the primary source of navigation in the User Interface (more specifically for the Code Comprehension exercises page for the student, and statistics for the Teacher; it must be made clear this dashboard will be used on other pages, as well). | Dashboard Component | Develop a primary navigation component for the UI, serving as the main navigation hub for both students and teachers. |  | 3 React State hooks (for email, password, and user agreement to Terms & Conditions) should be created within the component to track the input fields’ states at all times. | React State Hooks | Implement state management for email, password, and terms agreement using React hooks. |  | 2 React State hooks (for email and password) should be created within the component to track the input fields’ states at all times. | React State Hooks | Implement state management for email and password using React hooks. |  | Ensure that the teacher’s page is rendered properly. | Teacher Page Rendering | Verify that the teacher's page is displayed correctly and functions as intended. |  | Add a React component called DescriptionBox, and an appropriate route (/dashboard) via React Router for the Dashboard page. A React State Hook should be attached to this component to monitor state. | DescriptionBox Component | Develop a DescriptionBox component with state monitoring, linked to the /dashboard route. | [2] |  | Define a function that checks if the provided text is not an explanation (random text, etc.) or cannot constitute a valid attempt. This function will cause Prometheus to send an error message to the student via the chat interface and will ask them to try again (this may reuse or implement reusable functionality). | Explanation Validity Checker | Implement a function to validate explanations, triggering an error message through Prometheus if invalid. | [2] |  | Implement the requisite navigatory tools (or rather update the stubs that have been outlined in the “Barebones” Epic). | Navigatory Tools Update | Update navigational elements as per the "Barebones" specifications. | [2] |  | Leverage functions that have been outlined in the “As a student, I want to view a summary of my progress in the code comprehension progress as a whole, so that I can understand how well I understand the material,” and create a wrapper function (following DRY principles). | Progress Summary Wrapper Function | Adapt existing functions for summarizing code comprehension progress, encapsulating them in a single, reusable wrapper function. |  | Leverage functions that have been outlined in the “As a student, I want to view a summary of my progress in the code comprehension progress as a whole, so that I can understand how well I understand the material,” user story and perform appropriate arithmetic operations. | Progress Summary Calculation Functions | Adapt existing functions for summarizing code comprehension progress, incorporating arithmetic operations as per the user story requirements.
| Create reusable React components called NavigationButton. | NavigationButton Component | Design reusable navigation buttons throughout the application, customizable for different user types and functionalities. |  | A JavaScript function should be created to check for the sign-up conditions listed above on form submission, before sending the data to the server. | Validation Function | Develop a validation function to verify sign-up conditions upon form submission. |  | A JavaScript function should be created to check for the log-in conditions listed above on form submission, before sending the data to the server. | Validation Function | Develop a validation function to verify login conditions upon form submission. | [5 empty] | Create a scrollable React component that displays the code snippet, generated code, and the user-provided description. Create appropriate State Hooks. This will be implemented in accordance with the UI mockup. | Scrollable Code Display Component | Implement a scrollable component to show code snippets, generated code, and user descriptions, with state management. | [4] |  | Implement a function that when the send explanation button is clicked, sends a POST request to the server which in turn sends a request invoking Ollama’s code generation. | Send Explanation Function | Develop a function to send explanations to the server, initiating code generation via Ollama. | [2] |  | Define a React Component that is able to render all the information outlined in DOD | Information Rendering Component | Create a React component capable of displaying all required information as per the Definition of Done (DOD). | [3] |  | Create a React component that displays this information in a predetermined format. | Progress Summary Display Component | Develop a React component designed to present the progress summary in a structured layout. |  | Create a React component that displays this information in a predetermined format. | Progress Summary Display Component | Develop a React component designed to present the progress summary in a structured layout, adhering to the predetermined format.
| Create a separate Dashboard instance (use extensions from Dashboard) for the students and populate it with the necessary buttons for the respective user type (student). The “necessary buttons” are conjoined with other user stories e.g. The ability to view statistics requires you to have a proper button. However, this does not require that functionality to be completed i.e. it can be a stub (until it is implemented). A comprehensive enumeration is omitted as it can be discerned from the other user stories, though the most pressing buttons and their necessary routes are outlined below. | Extended Dashboard for Students | Extend the Dashboard component for student-specific needs, including student-specific buttons and routes. Initial versions can be stubs until full functionality is implemented. |  | Another JavaScript function should be created to handle the form submission (the transfer of data from the client to the server) via a POST request. | Form Submission Handler | Implement a function to manage form submission, including data transfer to the server. |  | Another JavaScript function should be created in order to handle the form submission (the transfer of data from the client to the server) via a POST request. | Form Submission Handler | Implement a function to manage form submission, including data transfer to the server. | [5 empty] | Add a React component with a Button to send their explanation over to Ollama for code generation on click (making a POST request to invoke code generation, described below in the API specification). Use a React State Hook here, as well. | Code Generation Button Component | Create a button component for submitting explanations to generate code, incorporating state management. | [2] |  | The generated code will be run against the retrieved unit tests by dynamically inserting the tests into a test function within the server, and creating an object storing necessary information i.e. the test name and success/failure. | Generated Code Testing | Execute the generated code against predefined tests, capturing test outcomes. | [4] |  | Make a GET request to /users/:userID using the id that is already available in the current client session by virtue of them being logged in. Make a GET /codeSnippets/:codeSnippetID request as well as the code snippet itself isn't stored alongside the user. Both calls are needed for appropriate rendering (please view Data Specifications). | User and Code Snippet Retrieval | Perform GET requests to fetch user and code snippet data based on available IDs. | [4]
| Create a separate Dashboard instance (use extensions from Dashboard) for the teacher(s) and populate it with the necessary buttons for the respective user type (teacher). The “necessary buttons” are conjoined with other user stories e.g. The ability to view statistics requires you to have a proper button. However, this does not require that functionality to be completed i.e. it can be a stub (until it is implemented). A comprehensive enumeration is omitted as it can be discerned from the other user stories, though the most pressing buttons and their necessary routes are outlined below. | Extended Dashboard for Teachers | Similar to the student version, extend the Dashboard component for teacher-specific needs, tailored for teacher functionalities like managing classes or viewing reports. Initial versions can also be stubs. |  | Once the server receives the data from the client, it should call Firebase Authentication’s helper function to handle the authentication process. | Server-side Authentication | On receiving data, invoke Firebase Authentication functions for processing. |  | When the data is passed down to the server, the server should call Firebase Authentication’s helper function to handle the authentication process. | Server-side Authentication | On receiving data, invoke Firebase Authentication functions for processing. | [5 empty] | Implement a function to ensure that the DescriptionBox is not “empty”, so as to prevent unnecessary sends. (Empty can mean only white-space also.) | Empty Check Function | Develop a function to validate the DescriptionBox content before submission. | [1] |  | Define a React Component that displays the above information in a pre-defined format to the student. | Test Result Display Component | Create a React component to present test results to the student in a structured manner. | [3] |  | Using the returned data from the request, display this data in a UI/UX-friendly format on the React Component defined above. | Data Display Enhancement | Utilize the fetched data to enhance the UI/UX of the React component, presenting it in a user-friendly manner. | [3]
| Attach and define a function to the buttons for the Student dashboard, which on button click, allows the student(s) to navigate to the attached route (a specific “route” or path (that uses a hyperlink) to a different part of the application e.g. The statistics page. The button name and hyperlinks will be provided as React component props). | Button Navigation Functionality for Students | Implement navigation functionality for student-specific buttons, enabling students to navigate to relevant parts of the application. |  | Then, a document containing the username and auto-generated ID should be created using Cloud Firestore’s imported library function inside the ‘users’ collection in the Cloud Firestore database. | Document Creation in Firestore | After authentication, create a new document in Firestore with user details. |  | Once the request is resolved by the server, the user should receive a success alert in the UI, indicating that the log-in was successful. They will then be redirected to the Dashboard. | Success Alert and Redirection | Display a success alert upon successful authentication and redirect the user to the dashboard. | [5 empty] | Present the student with a sample code snippet from the database (using the GET request to /codeSnippets in the Firebase database) based on | Sample Code Snippet Presentation | Fetch and display a sample code snippet from Firebase, either by default or based on user selection. | [3] |  | A PUT request will be sent using the student’s ID to update the relevant code-snippet information (refer to the data section) and other relevant Data (such as their Progress on the Code Snippet). | Update Code Snippet Information | Implement a PUT request to update code snippet details and progress based on the student's ID. | [2]
| Attach and define a function to the buttons for the Teacher dashboard, which on button click, allows the teacher(s) to navigate to the attached route (a specific “route” or path (uses a hyperlink) to a different part of the application. The routes overlap with the enumeration above. | Button Navigation Functionality for Teachers | Implement navigation functionality for teacher-specific buttons, tailored to their roles and responsibilities, allowing them to navigate to relevant parts of the application. |  | Once the document is created successfully, an alert should pop up in the UI, notifying the student that the sign-up was successful. | Success Alert Notification | Display a success alert upon successful document creation in Firestore. | [9 empty] | The default snippet (by ordinality). | Default Snippet Selection | Automatically select a default code snippet based on its ordinal position. | na
| Ensure that each page has a logical connection to another page, so that a situation does not arise that strips the user of the ability to navigate the application. | Application Navigation Logic | Maintain logical connections between pages to ensure seamless navigation and prevent users from getting lost or unable to navigate effectively. |  | Implement a mechanism to redirect the user to the dashboard. | User Redirection | Redirect the user to the dashboard after successful sign-up completion. | [9 empty] | Or their preference (by selection). | Custom Snippet Selection | Allow the student to choose a code snippet from a list. | na
REST API not for Ollama but definitely for the application. Frontend and Backend needs to be functional | [16 empty] | Implement appropriate functions, buttons (re-using existing React components), and an extensible and collapsible list to allow the student to indicate preference i.e. select a snippet and ensure that the correct snippet is loaded. | Snippet Preference Selector | Provide a mechanism for selecting a code snippet, reusing components and ensuring the selected snippet is loaded. | [3]
[17 empty] | The codeSnippetId received from the GET request should be stored in a React Component. A React State Hook should be attached here as well, to update the code snippet if the user wishes to change it. | Dynamic Code Snippet Management | Manage the selected codeSnippetId within a React component, updating the snippet as needed. | [1]
[17 empty] | Implement rudimentary functionality to test for a “lazy” response. A function will be implemented with several helper functions which will parse the student description to check if the provided description is “lazy” or not. For an explanation of “lazy” please see the clarification above. | Lazy Response Detection | Develop a function to assess the quality of the student's description, identifying "lazy" responses. | [4]
[17 empty] | Ensure that Firebase’s database is updated, as necessary. | Database Update Mechanism | Implement functionality to update the Firebase database as required by user actions. | [1]